## Sheet1
Timestamp | Sample Question 1 | Sample Question 2
|  |  | DevFortress | Sprint No | 1 | 2
|  | ID | Description |  | Time
|  | 1 | Planning & Analysis requirements
|  | 2 | UML diagram
|  | 3 | Model Implementation
|  | 3.1 | Player
|  | 3.1.1 | Player can hire developer/employee
|  | 3.1.2 | Player can accept/cancel project
Player get half of the money when accept
Player get the other half when finish the project
Player lose the money they get when accept the project + 1/3 of the total money of the project when project fail or cancelled
|  | 3.1.3 | Player can fire developer/employee
|  | 3.1.4 | Player can buy items (computer, coffe, pizza) |  | 1
|  | 3.2 | Skills
|  | 3.3 | Developers
|  | 3.3.1 | Developer has some random skills point when generated
|  | 3.3.2 | Developers have Happiness
|  | 3.3.3 | Developers have a list of skills and those skills' level (maybe use map) |  | 2
|  | 3.3.4 | Developer do not work without pizza, coffee
Developer's happy when have beer
Developers may leave if they are unhappy
|  | 4 |  |  | 3
|  | 5 | Event occure every week
|  | 5a | Event happen
|  | 7 | Player can buy pizza, coffee, beer. Developer can consume them
7a
|  | 7b | Developer produce half function point when have beer
7c
|  | 2 | Graphic User Interface(Detail need)
|  | 2a | Happy bar
|  | 2b | Dialog to show all skill point of developers
|  | 2c | Dialog show employee improve a particular skills
|  | Sprint 1 |  |  | 6
8
9
10
11
12
13
14
|  | Sprint 2 |  |  |  | 0
We start to develop the project from week 2 and the first sprint finish on Sunday of Week 5 (17/11/2012). The unit using in the estimation in Sprint backlog is "day", so that 28 is the maximum for sprint 1. We have to choose the feature that allow us to finish on time, we can add feature if we have enough time
(Any comment or ideal here)

## Sheet2
ABBC Team
| Team members | Name | ID
|  | Tran Tuan Anh | s3269999
|  | Dang Thanh Binh | s3299600
|  | Dang Quang Binh | s3274973
|  | Hoang Huy Cat | s3275199
SPRINT BACKLOG
| DevFortress |  |  | Sprint No | 1
Story ID | Story task |  |  |  | Time
1 | Planning & Analysis requirements |  |  |  | 2
| Create Product Backlog from requirement |  |  |  | 0.5
| Create Sprint Backlog |  |  |  | 0.5
| Create UML diagram (Class diagram) |  |  |  | 1
2 | Create basic model skeleton and classes |  |  |  | 5
| Use Facade Patent Design for Model - Create Model interface |  |  |  | 1
| Create Sub-classes and their method |  |  |  | 4
3 | Implement statergy patern: the longer user plays, the more chance they get the difficult project |  |  |  | 2
| System auto generate employee that more skilled when user in difficult mode |  |  |  | 1
| System auto generate project with high level when the game getting more difficult |  |  |  | 1
4 | Player can accept/cancel project, when cancel project, player looses money, |  |  |  | 1
| System generate the the list of projects, and the requirement skills for each project |  |  |  | 1
5 | User can hire and fire employees |  |  |  | 1
| System will generate the list of employee when player want to hire a new employee |  |  |  | 0.5
| (Assume, we'll change at sprint 2) System will buy computer automatically if company doesn't have enough for employee |  |  |  | 0.5
6 | Pay Salary at the end of each turn |  |  |  | 0.5
| System calculate salary base on each employee skills and subtract from user's capacity |  |  |  | 0.5
7 | End Game Condition
| System compare the capacity, game over when user's capacity is less than or equal zero |  |  |  | 0.5
9 | Calculate function points produced by employee each turn |  |  |  | 0.5
| Check if the project succeeds or fails |  |  |  | 0.5
10 | Graphic User Interface |  |  |  | 6
| Use Swing for creating all element of the GUI |  |  |  | 5.5
| Connect with model using MVC model |  |  |  | 0.5
11 | Draw basic UI mock-up with Balsamiq and paper
12 | Draw main screen UI in code |  |  |  | 1
13 | Draw pop-up Dialogs for program's function such as list of projects etc. |  |  |  | 1
2